## Sheet1
				Remaining Effort (hrs) / Sprint Timeline

		ss

Day0	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8
192	176	144	112	80	48	16	0	0
198	176	145	112	82	50	17	0	0

192	168	148	123	95	64	40	0	0
198	140	112	77	62	4	9	2	0

## Sheet2
Story #	Feature	Sprint Backlog Item	Task #	Volunteer	Task Details	Initial Effort Estimate (hrs)	New Estimates of Effort remaining at end of					Status
				Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8
US001	Register and login Customer	As a Customer I am able to register and login to the website	Task 1	Mukhesh Sure	Code Review	4	2	2					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	2					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	1		1			Completed
				Completed
US002	Register and Login Admin/Employee	As a Admin/Employee, I am able to register and login to the website	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2		1		1					Completed
			Task 6	Ruchitha s	Execute the tests	5	1		1	2	1				Completed
				Completed
US003	Coustomer Check Balance	As a customer,My Should be able to view my details and Balance	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2		1		1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US004	Coustomer Withdraw and Deposit	As a Coustomer,I Should to able to perform withdraw and Deposit Money	Task 1	Mukhesh Sure	Code Review	6	2	1	1	2					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1			1			Completed
			Task 5	Ashwini Yadav	Defect fixing	2		1		1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US005	Employee Create and Delete	As a Employee, I Should be able to Perform Create and Delete Operations on Coustomers	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2		1		1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US006	Employee Read and Update	As a Employee, I Should be able to Perform Read and Update Operations on Coustomers	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US007	Admin Create and Delete	As an Admin, I Should be able to Perform Create and Delete Operations on Coustomers	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	5			1	2		1	1		Completed
				Completed
US008	Admin Read and Update	As an Admin, I Should be able to Perform Read and Update Operations on Coustomers	Task 1	Mukhesh Sure	Code Review	4	2	1				1			Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US009	Employee Logout	As an Employee, I should to safely Exit out of system if I entered any Wrong choice.	Task 1	Mukhesh Sure	Code Review	7	2	1		1		2	1		Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1				2				Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US010	Coustomer Logout	As an Coustomer, I should to safely Exit out of system if I entered any Wrong choice.	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US011	Random Genrator	Employee Id's and Coustomer Id's Should be Managed And Auto Genrated By the System	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	3	1	1	1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US012	Validation Util	Data Entered is Validated According to the Constrients	Task 1	Mukhesh Sure	Code Review	3		1			1	1			Completed
			Task 2	Dhanraj Shinde	HTML CSS Javascript	2	1		1					Completed
			Task 3	Shivam Mishra	HTML CSS Javascript	2				2					Completed
			Task 4	Jatin Rastogi	Testing	1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2			2					Completed
			Task 6	Ruchitha s	Execute the tests	3				1		2			Completed
				Completed
				Total	198	58	28	35	62	4	9	2		Completed